## Executve Summary
Sao Tome and Principe NDC Implementation Plan
Date of translation: |  |  | September 2018
Plan Overview
Plan Components | Number |  |  | Plan's Resources | Budget
Outcomes | 11 |  |  | Existing initiatives and projects | 23805375
Outputs | 45
KPIs | 175 |  |  | New initiatives and projects | 85831545
Adaptation | 76
Mitigation | 58 |  |  | Total | 109636920
Cross-cutting | 41
Legend:
Categorization of KPIs (for tracking purposes)
Covered by existing initiatives and projects | KPIs related to ongoing projects and initiatives.
Ongoing | KPIs in implementation.
Concluded | KPIs Completed.
New | KPIs in the plan that do not have corresponding actions initiated.
Planned | KPIs that are foreseen to be completed in the execution of projects and initiatives with planned resources
No resources/Expected support | KPIs without resources / expected support, therefore, priority for support in new initiatives
Tables and detailed data
| Number |  |  |  | Budget*
Marks/Indicators | Planned | Ongoing | Concluded | No resources/Expected support
Adaptation | 19 | 11 | 0 | 46 | 44695500
Mitigation | 25 | 14 | 0 | 19 | 61841420
Cross-cutting | 6 | 9 | 1 | 25 | 3100000
| Number |  |  |  | Budget*
Marks/Indicators | Planned | Ongoing | Concluded | No resources/Expected support
Agriculture | 3 | 2 | 0 | 2 | 756000
Water | 0 | 2 | 0 | 4 | 1190000
Construction | 3 | 0 | 0 | 6 | 10280000
Energy | 6 | 11 | 0 | 14 | 46753000
Forestry | 24 | 1 | 0 | 8 | 14264545
Industry | 0 | 0 | 0 | 0 | 0
Multi-sectoral | 7 | 17 | 1 | 46 | 12412500
Fishery / Oceans | 4 | 0 | 0 | 7 | 2102000
Waste | 0 | 1 | 0 | 1 | 628875
Transport | 2 | 0 | 0 | 1 | 21250000
Tourism | 0 | 0 | 0 | 1 | 0
Organizations with initiatives included in the Implementation of the Plan
Note on H64: Incluí orçamento de projetos em execução e planejados com informação disponibilizada.
Note on H71: Incluí orçamento de projetos em execução e planejados com informação disponibilizada.

## Partnership Plan
Outcomes | Outputs | KPIs | Status | Conclusion date | Sector | Focus | Organization / Institution leading the Implementation and related projects / initiatives / programs | Comments | Performance summary report | Interface with government (Ministry / Board) | International Partner Focal Point | Government Focal Point | Project name | Estimated budget | Other Projects / Initiatives / related programs | Coordination Plan | Cronograma
[17 empty] | 2018 | [5 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021
[17 empty] | M7 | M8 | M9 | M10 | M11 | M12 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
Expansion to 47% of the renewable energy supply: - Hydroelectric power plant connected to national distribution network (9 MW) - Small hydroelectric power plants (4 MW) - Photovoltaic panels (12 MW) "Expansion to 47% of the renewable energy supply: - Hydroelectric power plant connected to national distribution network (9 MW) - Small hydroelectric power plants (4 MW) - Photovoltaic panels (12 MW) | Institutional environment for investments and sector databases strengthened to promote renewable energies | National renewable energy potential mapped and published | Ongoing | 2019 | Energy | Mitigation | PNUD/GEF SEFA/BAD | _Potencial hidroeletrico de Principe realizado _Estudos de aproveitamento hidrologico de 14 bacias em S.Tomé realizados _Estudos aprofundados sobre duas bacias hidrográficas na Ilha de São Tomé (ainda a definir) | PNUD/GEF SEFA/BAD | DGRNE/MIRNA | Maite Mendizabal | Gilmar Ramos | 94537-Projeto Energy | 500000
|  | Tariff study for the electric sector elaborated | Ongoing | 2021 | Energy | Mitigation | Banco Mundial e Banco Europeo de Investimento |  |  |  | Nicolas Jean Marie Sans |  | STP Power Sector Recovery Project | 200000
|  | Cost of Renewable Energy for the final consumer in the different energy development strategies calculated and published |  |  | Energy | Mitigation
|  | Study of projected future energy demand in STP elaborated and published | Ongoing | 2021 | Energy | Mitigation | Banco Mundial e Banco Europeo de Investimento |  |  |  | Nicolas Jean Marie Sans |  | STP Power Sector Recovery Project | 100000
|  | Studies and databases of the Energy sector compiled and analyzed |  |  | Energy | Mitigation
|  | Studies and databases of the Energy sector published and accessible |  |  | Energy | Mitigation
|  | Studies of the Energy sector reviewed (if identified the need on previous assessment) |  |  | Energy | Mitigation
|  | Strategic Plan for the Energy Sector developed and consultation process carried out | Ongoing | 2021 | Energy | Mitigation | Banco Mundial e Banco Europeo de Investimento |  |  |  | Nicolas Jean Marie Sans |  | STP Power Sector Recovery Project | 400000
|  | Strategic Plan for the Energy Sector approved by the government | Ongoing | 2021 | Energy | Mitigation | Banco Mundial e Banco Europeo de Investimento |  |  |  | Nicolas Jean Marie Sans
|  | Renewable Energy Strategic Plan elaborated | Ongoing | 2019 | Energy | Mitigation | PNUD/GEF |  |  | DGRNE/MIRNA | Maite Mendizabal | Gilmar Ramos | 94537-Projeto Energy | 100000
|  | Renewable Energy Strategic Plan approved by the government | Ongoing | 2019 | Energy | Mitigation | PNUD/GEF |  |  | DGRNE/MIRNA | Maite Mendizabal | Gilmar Ramos | 94537-Projeto Energy | 3000
|  | New regulation of the energy sector developed and consultation process carried out | Ongoing | 2021 | Energy | Mitigation | MIRNA/DGRNE;MADR/DF/DA | [5 empty] | Promoção da Energy hídroeletrica de forma sustentavel e resiliente ao clima atraves duma abordagem que integra gestão de terras e florestas | 5200000
|  | Regulamentação do setor energético desenvolvida e processo de consulta popular realizado | Ongoing | 2019 | Energy | Mitigation | PNUD/GEF | _Regulamentação da Lei do Sector Elétrico para incluir a produção de Energys renováveis em curso _Regulamentação do Regime Sancionatório e Manual de Qualidade de Serviço do setor elétrico em curso _Regulamentação da Interligação e relações de compra-venda do setor elétrico em curso |  | DGRNE/AGER/MIRNA | Maite Mendizabal | Gilmar Ramos | 94537-Projeto Energy | 60000
|  | New regulation of the energy sector approved by the government |  |  | Energy | Mitigation
|  | Professional training plan for national energy technicians elaborated and implemented with periodic evaluation of results | Planned | 2022 | Energy | Mitigation | BAD/FAD | Incluido no projeto Energy do BAD/FAD |  |  | Elizabeth MUGUTI, Ceutonia Lima |  | Infraestrutura de apoio à Water e Energy | 14000000
|  | Professional training plan for national energy technicians elaborated and implemented with periodic evaluation of results | Ongoing | 2018 | Energy | Mitigation | BM/BEI PNUD/GEF | _Plano de formação AGER e EMAE em elaboração e prevista entrega para setembro2018 (BM) _Plano de formação DGRNE e outras entidades (DGA, Min Finanças, Região A. Principe) a ser elaborado (PNUD) _Identificação das necessidades em matéria de formação profissional para o sector em curso (DGRNE + Ministério de Educação) _Implementação dos programas de formação prevista para 2019-2021 (PNUD, BM) |  | DGRNE DGA MINISTERIO DE EDUCAÇÃO | Maite Mendizabal | Gilmar Ramos | 94537-Projeto Energy | 200000
|  | Training plan for other relevant ministries's technicians (Environment, Finance, etc.) on the different aspects related to the energy sector elaborated and implemented | Planned |  |  | Mitigation | PNUD/GEF |  |  | DGRNE DGA MINISTERIO DE EDUCAÇÃO | Maite Mendizabal | Gilmar Ramos | 94537-Projeto Energy
|  | River basin regulation considering multiple uses and promotion of the hydro-energy sector elaborated and approved |  |  | Energy | Mitigation |  | _Plano de Gestão Integral de Recursos Hídricos elaborado (DGRNE) _Definição de Planos operativos anuais de implementação deste grande plano ainda não realizada |  | DGRNE/MIRNA
| Investment in renewable energies promoted | List of renewable energy investment projects prioritized by the government | Planned | 2022 | Energy | Mitigation | MIRNA/EMAE | [5 empty] | Promoção das Mini-Hídricas para a produção de Energy limpa e gestao da Water | 14300000
|  | National system of incentives to promote private investment in the electric sector developed | Planned |  | Energy | Mitigation | PNUD/GEF |  |  | Min Finanças, Comercio e Economia Azul (MFCEA) | Maite Mendizabal | Gilmar Ramos | 94537-Projeto Energy | 15000
|  | Manual of operational procedures (technical and administrative) for the investment in Renewable Energies elaborated and published | Planned |  | Energy | Mitigation | PNUD/GEF |  |  | Min Finanças, Comercio e Economia Azul (MFCEA) | Maite Mendizabal | Gilmar Ramos | 94537-Projeto Energy | 25000
|  | "One-stop-shop" for investment projects developed for the energy sector | Planned |  | Energy | Mitigation | PNUD/GEF |  |  | Min Finanças, Comercio e Economia Azul (MFCEA) | Maite Mendizabal | Gilmar Ramos | 94537-Projeto Energy | 50000
|  | Technical feasibility, environmental, social and economic projects studies selected and undertaken | Planned | 2019 | Energy | Mitigation | BAD/SEFA |  |  |  | Thomas Micholitsch, Ceutonia Lima |  | Infraestrutura de apoio à Water e Energy | 1000000
|  | Number of priority Projects for Renewable Energy Investment prepared |  |  | Energy | Mitigation
|  | Priority renewable energies investment projects presented to national and international investors |  |  | Energy | Mitigation
| Renewable energy supply expanded in STP | Contador power plant reformed and capacity expanded to 2.2 MW | Ongoing | 2021 | Energy | Mitigation | Banco Mundial e Banco Europeo de Investimento |  |  |  | Nicolas Jean Marie Sans |  | STP Power Sector Recovery Project | 10600000
| Strategy and plan to transform Principe Island into a reference in renewable generation and energy efficiency elaborated | Renewable Energy and Energy Efficiency Plan for the Principe Island developed |  |  | Energy | Mitigation
|  | Budgeting and investment plan for the Principe Island Plan developed |  |  | Energy | Mitigation
|  | Investment Plan presented (road show) for national and international investors |  |  | Energy | Mitigation
Illegal and indiscriminate felling of trees reduced by 15% | Strengthened restrictive measures and effective monitoring of illegal felling of trees | Forestry Law and PNDF implemented (specify this activity) |  |  | Forestry | Mitigation
|  | Ranger team expanded and decentralized to STP's districts - Number of guards and geographic location |  |  | Forestry | Mitigation
|  | Awareness and education program for deforestation and forest degradation implemented involving policy makers and society (qualitative and quantitative descriptions of activities) | Planned | 2021 | Forestry | Mitigation | BAD /GEF / PRIASA II |  |  | DGA/DADA/ADAPPA/CADR | Jean-Marie Meng, Ceutónia Lima |  | Reforço da resiliencia e da capacidade de adptação às mudanças climáticas em São Tomé e Príncipe | 25000
|  | Number of institutional partnerships for forestry oversight (eg army) |  |  | Forestry | Mitigation
|  | Updated National Forestry Inventory published | Planned | 2020 | Forestry | Mitigation | PNUD/GEF | Novo projeto Biodiversidade PNUD/GEF inclui esta atividade |  | Direcção das Florestas/MADR Direção Geral de Ambiente /MIRNA | Maite Mendizabal | Anahory Dias | Projeto BIODIVERSIDADE | N/A
| Collaborative monitoring and evaluation system for forest resources implemented | National Collaborative Forestry and Landscaping Monitoring System established and operational, in close partnership | Planned | 2023 | Forestry | Mitigation | FAO/GEF |  |  | Direcção das Florestas/MADR |  | Lourenço Monteiro | Landscape Restoration for Ecosystem Functionality and Climate Change Mitigation in the Republic of São Tomé e Príncipe | 4666515
|  | Partners involved in the FAO / GEF project are available to participate in the collaborative M & A system | Planned | 2023 | Forestry | Mitigation | FAO/GEF |  |  | Direcção das Florestas/MADR |  | Lourenço Monteiro
| Alternatives for the indiscriminate and ilegal use of wood mapped and promoted | Mapping study of wood and forest uses in STP published |  |  | Forestry | Mitigation
|  | Study of economic alternatives to wood exploitation elaborated and published | Planned | 2019 | Forestry | Mitigation | BAD /GEF / PRIASA II |  |  | Direção geral do Ambiente | Jean-Marie Meng, Ceutónia Lima |  | Reforço da resiliencia e da capacidade de Adaptation às mudanças climáticas em São Tomé e Príncipe | 15000
|  | Study and implementation of alternative methods to wood for Construction and energy consumption elaborated |  |  | Forestry | Mitigation
|  | Evaluation of potential REDD and Payment for Environmental Services carried out |  |  | Forestry | Mitigation
Forest and Landscape Restoration Policies (FLR) developed and restoration programs and complementary activities implemented | Improved national commitment to Forestry and Landscape Restoration in São Tomé and Príncipe | National Forestry Landscape Restoration Platform established and operational to support and guide the work of the RFP, including interested institutions, private sector, civil society, local communities and partner projects. | Planned | 2023 | Forestry | Mitigation | FAO/GEF |  |  | Direcção das Florestas/MADR |  | Lourenço Monteiro | Landscape Restoration for Ecosystem Functionality and Climate Change Mitigation in the Republic of São Tomé e Príncipe | 4666515
|  | Forestry Directoracte trained to produce a Forestry Landscape Restoration Plan to inform and guide future Forestry, Conservation and Restoration management initiatives in STP (number of technicians trained and assessment of capacities) | Planned | 2023 | Forestry | Mitigation | FAO/GEF |  |  | Direcção das Florestas/MADR |  | Lourenço Monteiro
| Improved policy framework for conservation, restoration and sustainable management of STP's forests. | Guidance document / model for improved RFP policies including recommendations based on policy analysis, gaps, laws and regulations on forest management, conservation and elaborated RFP. | Planned | 2023 | Forestry | Mitigation | FAO/GEF |  |  | Direcção das Florestas/MADR |  | Lourenço Monteiro
|  | Approved laws, regulations and incentives. | Planned | 2023 | Forestry | Mitigation | FAO/GEF |  |  | Direcção das Florestas/MADR |  | Lourenço Monteiro
| Participatory interventions to improve ecosystem services and mitigate climate change in vulnerable natural forest areas in STP promoted | 4,500 hectares of the Contador river basin restored in partnership with the World Bank-supported Energy Sector Recovery Project (PRSP). | Planned | 2023 | Forestry | Mitigation | FAO/GEF |  |  | Direcção das Florestas/MADR |  | Lourenço Monteiro
|  | 23,000 hectares of natural forests restored and managed sustainably in degraded areas of STP. | Planned | 2023 | Forestry | Mitigation | FAO/GEF |  |  | Direcção das Florestas/MADR |  | Lourenço Monteiro
|  | 600 hectares of STP mangrove areas restored and managed for conservation and recreation purposes. | Planned | 2023 | Forestry | Mitigation | FAO/GEF |  |  | Direcção das Florestas/MADR |  | Lourenço Monteiro
| Improved utilization of forest resources for the benefit of local communities living in sensitive landscapes of Sao Tome and Principe | 7,150 hectares of shade forests supporting high-quality agroforestry plantations are restored and managed in a sustainable manner in the protection zones of the Obô and Príncipe Natural Parks | Planned | 2023 | Forestry | Mitigation | FAO/GEF |  |  | Direcção das Florestas/MADR |  | Lourenço Monteiro
|  | Number of "Intelligent Wood Processing Pilot Centers", using portable sawmills, such as an implanted public-private partnership | Planned | 2023 | Forestry | Mitigation | FAO/GEF |  |  | Direcção das Florestas/MADR |  | Lourenço Monteiro
|  | Income-generating activities related to the production, processing and sale of PFNL promoted to 650 beneficiaries from 4 rural communities on both islands, based on replication of existing experiences and capacity building. | Planned | 2023 | Forestry | Mitigation | FAO/GEF |  |  | Direcção das Florestas/MADR |  | Lourenço Monteiro
| Lessons learned and best practices related to the TRI (The Restoration Initiative) disseminated among the relevant public | Information management center for knowledge management created and operational through a partnership agreement with national actors | Planned | 2023 | Forestry | Mitigation | FAO/GEF |  |  | Direcção das Florestas/MADR |  | Lourenço Monteiro
| Planting of forest species promoted | National reforestation plan developed |  |  | Forestry | Mitigation
|  | Research to introduce trees to Adaptation to drylands and savannas completed |  |  | Forestry | Mitigation
|  | Hectares of integrated agro-forestry-graising systems implemented and evaluated | Ongoing | 2020 | Forestry | Mitigation | PNUD/GEF | _Programa de reflorestação (agroForestry) em Claudino Faro concluido (70Ha- 2017) _Programa de reflorestação em 100 Há. (Cantagalo e Mezochi em 2018) _Programa de Reflorestação do projeto Adaptation (x Ha.) _Construidos 3 viveiros (2 em São Tomé e 1 em Principe) _Mais Há a ser programadas até fim do projeto em parceria com stakeholders |  | Direcção das Florestas/MADR | Maite Mendizabal | Anahory Dias | 94537-Projeto Energy | 200000
|  | Hectares of reforestation with species of commercial value and fast growth implemented | Planned | 2021 | Forestry | Mitigation | BAD /GEF / PRIASA II |  |  | Direção das Florestas/CADR | Jean-Marie Meng, Ceutónia Lima |  | Reforço da resiliencia e da capacidade de adptação às mudanças climáticas em São Tomé e Príncipe | 25000
Reduced use of nitrogen fertilizers in agriculture | Reduced use of nitrogen fertilizers in agriculture | Study of bio-fertilizers and composting techniques elaborated and published | Ongoing | 2019 | Waste | Mitigation | EU/CDMZ |  |  | MADR/CADR/CDAG/CDMZ |  | Helcikia Santos | Todos e todas protegemos o meio ambiente de Mé Zóchi | 628875
|  | Training of farmers and horticulturists for the implementation of good practices carried out and evaluation of participants' competences (number of trainings and trained farmers/horticulturists) | Ongoing | 2020 | Agriculture | Mitigation | PNUD/GEF | _Capacitação de técnicos extensionistas e agricultores na luta biologica contra a mosca da fruta _Capacitação a agricultores em uso eficiente insumos agrícolas, através do projeto Adaptation e do Projeto Energy |  | MADR/DADA | Maite Mendizabal | Armando Monteiro Dias | 91898 Projeto Adaptation | 50000
|  | Reinforcement of greenhouse production capacity | Planned | 2020 | Agriculture | Mitigation | BAD /GEF / PRIASA II |  |  | CIAT/MADR | Jean-Marie Meng, Ceutónia Lima |  | Elaboração do plano nacional de ordenamento do território da república de São Tomé e Príncipe, dos planos diretores distritais respetiva legislação de enquadramento e cartografia de referencia | 145000
|  | Land use planning for agriculture elaborated and approved | Ongoing | 2019 | Multi-sectoral | Cross-cutting | BAD / PNOT | Plano nacional de ordenamento de territorio elaborado |  |  | Jean-Marie Meng, Ceutónia Lima |  | Elaboração do plano nacional de ordenamento do território da república de São Tomé e Príncipe, dos planos diretores distritais respetiva legislação de enquadramento e cartografia de referencia | 2800000
Strengthened knowledge, analysis and institutional capacities to understand and manage climate risks in São Tomé and Príncipe | Basic information to subsidize climate risk management in São Tomé and Príncipe developed and updated | Geological map and STP soil maps updated |  |  | Multi-sectoral | Adaptation
|  | Map of fertility and agricultural potential developed for peri-urban areas of São Tomé and Príncipe (Mesquita, Uba-Cabra, Blu-blu, Amparo II, Saudade and Bom Sucesso) | Ongoing | 2018 | Agriculture | Adaptation | FAO |  |  | Ministério da Agriculture |  | Felizberto Cruz | Projeto de atualização da carta de fertilidade dos solos em sÃO tomé e Príncipe | 461000
|  | Installation of instruments for hydrological measurement in selected hydrological basins |  |  | Water | Adaptation
|  | Existing hydrometric data consolidated and shared | Ongoing | 2019 | Water | Adaptation | PNUD/GEF | _No âmbito do projeto Alerta Precoce, foram instaladas 32 estações hidro-meteorologicas em todo o territorio nacional, 2 centros de receção de dados no Instituto de Meteorologia e na DGRNE, capacitados os técnicos de ambas instituições e assinado protocolo com as Câmaras Distritais para manutenção das estações _A partilha de dados ainda não está sistematizada, sendo uma questão que deve ser urgentemente ressolvida. |  | MIRNA/INM (meteorologia) | Maite Mendizabal | João Vicente Lima (INM) | 86865 Projeto Alerta Precoce | 1150000
|  | System of measurement of oceanographic physical parameters as part of the strengthening of the coastal early warning system operationalized | Planned | 2023 | Fishery / Oceans | Adaptation | Banco Mundial | Planned Durante a primeira fase do projeto de Adaptation (PAMCZC), uma estação marítima foi instalada, os dados são coletados e armazenados pelo INM. Duas estações serão instaladas durante a segunda fase. |  | INM, DGA | Nicolas Desramaut | João Vicente Lima (INM) | WEST AFRICA COASTAL AREAS RESILIENCE INVESTMENT PROJECT (WACA) - PAMCZC II | 1500000
|  | Resources for maintaining the existing hydrometric network available |  |  | Water | Adaptation
| Understanding on climate risks and vulnerabilities in São Tomé and Príncipe strengthened | Multi-risk mapping and climate vulnerability of STP's communities carried out and made available on a geo-referenced basis | Ongoing | 2018 | Multi-sectoral | Adaptation | Banco Mundial | Um mapa de inundação para a ilha de STP está em preparação. |  | DGA, DNP, INM | Naraya Carrasco | Arlindo de Carvalho (DGA), Geisel de Menez (DNP) | Towards NDC Implementation in STP: Targeted Support to understand risks, plan for and mobilize funds towards building climate resilience | 100000
|  | Study of current water availability and demand in STP carried out |  |  | Water | Adaptation
|  | Study of availability and future demand for water resources in STP incorporating different scenarios of climate change carried out |  |  | Water | Adaptation
|  | Study of the impact of climate change on fishery resources and fishing activities and proposal of adapted fishing strategies / strategies completed |  |  | Fishery / Oceans | Adaptation
| Ability to Integrate Climate Change and Disaster Risk into Policy, Plans, and Country Projects strengthened | Number of qualified servers (by sector) and evaluation of server capacities (as part of training) | Ongoing | 2018 | Multi-sectoral | Adaptation | Banco Mundial |  |  | DGA, DNP, INM | Naraya Carrasco | Arlindo de Carvalho (DGA), Geisel de Menez (DNP) | Towards NDC Implementation in STP: Targeted Support to understand risks, plan for and mobilize funds towards building climate resilience | 50000
|  | Customized climate-change analysis and integration tool for government validated | Ongoing | 2018 | Multi-sectoral | Adaptation | Banco Mundial |  |  | DGA, DNP, INM | Naraya Carrasco | Arlindo de Carvalho (DGA), Geisel de Menez (DNP) | Towards NDC Implementation in STP: Targeted Support to understand risks, plan for and mobilize funds towards building climate resilience | 150000
| Climatic risks in coastal areas reduced | Study of Sustainable Construction Materials Alternative to Beach Sand and New "Inert Law" Completed | Planned | 2023 | Construction | Adaptation | Banco Mundial |  |  | DGA, D Geologia | Nicolas Desramaut | Arlindo de Carvalho, Edchilson das Neves Cravid | WEST AFRICA COASTAL AREAS RESILIENCE INVESTMENT PROJECT (WACA) - PAMCZC II | 230000
| Best practices adapted to the Agriculture and forestry in the context of climate change identified | Database with local and exotic species adapted to the diverse climatic conditions of STP elaborated | Planned | 2021 | Agriculture | Adaptation | BAD /GEF / PRIASA II |  |  | CIAT/CADR | Jean-Marie Meng, Ceutónia Lima |  | Reforço da resiliencia e da capacidade de adptação às mudanças climáticas em São Tomé e Príncipe) | 75000
|  | Results on experiments conducted with rural producers consolidated and published |  |  | Agriculture | Adaptation
|  | Manual of good practices for agricultural production and forestry in the context of climate change in STP developed and published | Planned | 2019 | Agriculture | Adaptation | BAD /GEF / PRIASA II |  |  | Ministério da Agriculture | Jean-Marie Meng, Ceutónia Lima |  | Reforço da resiliencia e da capacidade de adptação às mudanças climáticas em São Tomé e Príncipe) | 25000
Climate and Disaster Risk Reduced | Policy and legal framework for resilient management of coastal zones developed and resilience management plans developed | Concrete proposals to improve the regulatory framework for resilient management of coastal zones developed | Planned | 2023 | Multi-sectoral | Adaptation | Banco Mundial |  |  | DGA, Capitania, | Nicolas Desramaut | Arlindo de Carvalho | WEST AFRICA COASTAL AREAS RESILIENCE INVESTMENT PROJECT (WACA) - PAMCZC II | 150000
|  | Multi-sectoral coastal management plan in STP (including fishing, Tourism, Transports and Energy) prepared and approved | Planned | 2023 | Multi-sectoral | Adaptation | Banco Mundial |  |  | DGA, Dir Pescas, Dir Tourism, Capitania, Dir Transport | Nicolas Desramaut | Arlindo de Carvalho | WEST AFRICA COASTAL AREAS RESILIENCE INVESTMENT PROJECT (WACA) - PAMCZC II | 150000
| National policy and legislation for the management of disaster risk developed | National Policy for Risk and Catastrophic Management developed |  |  | Multi-sectoral | Adaptation
|  | National Policy for Risk and Disaster Management approved |  |  | Multi-sectoral | Adaptation
|  | Legislation for Risk and Catastrophe Management prepared |  |  | Multi-sectoral | Adaptation
|  | Legislation for Risk and Catastrophe Management approved |  |  | Multi-sectoral | Adaptation
| Regulations for the implementation of the "Inert" Law developed | Regulation for the Iner Law elaborated | Planned | 2023 | Construction | Adaptation | Banco Mundial |  |  | DGA, D Geologia | Nicolas Desramaut | Arlindo de Carvalho | WEST AFRICA COASTAL AREAS RESILIENCE INVESTMENT PROJECT (WACA) - PAMCZC II | 50000
|  | Regulation of InertLaw approved by the government |  |  | Construction | Adaptation
| National Platform for Disaster Risk Reduction created | National Platform for Disaster Risk Reduction elaborated |  |  | Multi-sectoral | Adaptation
|  | National Platform for Disaster Risk Reduction approved by the government |  |  | Multi-sectoral | Adaptation
|  | Members of the National Platform for Disaster Risk Reduction trained (number of training and assessment of capacities) |  |  | Multi-sectoral | Adaptation
| National Building Regulations and Codes for Resilient Housing and Infrastructure developed and approved | Legislative proposals on Construction of Resilient Buildings and Infrastructure Developed |  |  | Construction | Adaptation
|  | Legislative Proposals for Construction of Resilient Buildings and Public Infrastructure Approved |  |  | Construction | Adaptation
|  | Resilient Construction Code approved by the government |  |  | Construction | Adaptation
| Vulnerability reduced in selected communities: IO Grande (Gruta), Praia Melão (Mé-Zóchi), Pantufo, Micolo (Lobata), Pria Burra (Príncipe), Santa Catarina, Ribeira Afonso and Malanza. | Specific studies on target areas (ie geomorphology, sediment transport, currents, socio-economic assessments, channel capacities, sediment transport, etc.) completed | Planned | 2023 | Multi-sectoral | Adaptation | Banco Mundial |  |  | DGA | Nicolas Desramaut | Arlindo de Carvalho | WEST AFRICA COASTAL AREAS RESILIENCE INVESTMENT PROJECT (WACA) - PAMCZC II | 3100000
|  | Infrastructure to protect communities and assets in vulnerable coastal areas implemented | Planned |  | Multi-sectoral | Adaptation | Banco Mundial
| Vulnerability reduced in 6 selected communities: Ió Grande (Cave), Loxinga, Gamboa, Cruz (Agua Grande), Micolo, Abade e Santo António (Príncipe) | Specific studies on target areas (ie geomorphology, sediment transport, currents, socio-economic assessments, channel capacities, sediment transport, etc.) completed |  |  | Multi-sectoral | Adaptation
|  | Infrastructure to protect communities and assets in vulnerable coastal areas implemented |  |  | Multi-sectoral | Adaptation
| Conventional (concrete) protection infrastructure to protect public assets, tourist points and urban areas along the coast and rivers implemented in Agua Grande, Lembá and Lobata) Deployed | Studies and project for Água Grande completed | Ongoing | 2018 | Multi-sectoral | Adaptation | RVO - Dutch bilateral |  |  | DGA | Fenna Houkamp | Arlindo de Carvalho |  | 812500
|  | Protective infrastructure implemented in Água Grande | Planned | 2023 | Construction | Adaptation | RVO- EIB |  |  | DGA | Fenna Houkamp |  |  | 10000000
|  | Studies and project for Lembá completed |  |  | Multi-sectoral | Adaptation
|  | Protective infrastructure implemented in Lembá |  |  | Construction | Adaptation
|  | Studies and projects for Lobata completed |  |  | Multi-sectoral | Adaptation
|  | Protective infrastructure implemented in Lobata |  |  | Construction | Adaptation
| Voluntary Resettlements concluded in Selected Communities: Ió Grande (Gruta), Praia Melão (Mé-Zóchi), Pantufo, Micolo (Lobata), Praia de Burra (Príncipe), Santa Catarina, Ribeira Afonso and Malanza. | Preparatory studies for resettlement (socio-economic study, resettlement costs, definition and community approval of the resettlement area, etc.) completed | Planned | 2023 | Multi-sectoral | Adaptation | Banco Mundial |  |  | DGA | Nicolas Desramaut | Arlindo de Carvalho | WEST AFRICA COASTAL AREAS RESILIENCE INVESTMENT PROJECT (WACA) - PAMCZC II | 4800000
|  | Number of voluntary resettlement with built houses and service for basic infrastructure (water, light, sanitation, roads, etc.) | Planned |  | Multi-sectoral | Adaptation | Banco Mundial |  |  | DGA
| Voluntary Resettlement concluded in Selected Communities:: Ió Grande (Cave), Loxinga, Gamboa, Cruz (Water Grande). | Preparatory studies for resettlement (socio-economic study, resettlement costs, definition and community approval of the resettlement area, etc.) completed |  |  | Multi-sectoral | Adaptation
|  | Number of voluntary resettlement with built houses and service for basic infrastructure (water, light, sanitation, roads, etc.) |  |  | Multi-sectoral | Adaptation
| Center for Emergency Operations (COE) created and strengthened | COE Proposal approved by the government |  |  | Multi-sectoral | Adaptation
|  | Capacity building of COE staff and capacity assessment as part of training |  |  | Multi-sectoral | Adaptation
|  | Infrastructure and equipment for the COE installed and operational |  |  | Multi-sectoral | Adaptation
Increased climate resilience of communities and sectors of São Tomé and Príncipe. | Sectoral regulation for the integration of climate and disaster resilience into sectors developed and approved | Guidelines, Strategy and Action Plan to Enhance Cross-cutting Integration of Climate Change in Sector Policies | Ongoing | Fevereiro 2019 | Multi-sectoral | Adaptation | Consorcio QUAREIN/NIRAS, responsavel pela AT para a implementação do Projecto AMCC - Redução da Vulnerabilidade Climática em São Tomé e Principe |  |  | Comité Nacional para as Mudanças Climáticas (CNMC), DGA, DGPlano, DGPescas, DGAgriculture, DGFlorestas, DGUrbanismo, DGInfrastruturas, DGTransports, INE, INMG, PNO_ST e PNO_RAP | DUE Gabão, Albert Losseau | DGA, Eng. Lourenço Monteiro de Jesus | Projecto AMCC - Redução da Vulnerabilidade Climática em São Tomé e Principe | Valor total do projeto FAO/GEF USD 4,666,515
|  | Diagnosis of the institutional and legislative framework of climate change in STP with respect to the responsibilities, capacities and technical and financial means elaborated. | Ongoing | Agosto 2018 | Multi-sectoral | Adaptation | Consorcio QUAREIN/NIRAS, responsavel pela AT para a implementação do Projecto AMCC - Redução da Vulnerabilidade Climática em São Tomé e Principe | - Inventário dos mecanismos de integração da mudança climática existentes; - Inventário e análise do quadro legislativo relativo ao ambiente; - Análise dos mecanismos existentes e das categorias dos atores envolvidos na luta contra a mudança climática, identificação dos recursos disponíveis por entidade envolvida e análise dos textos legais relativos ao ambiente; - Identificação das restrições/limitações que podem impedir a efetiva integração da mudança climática. |  | Comité Nacional para as Mudanças Climáticas (CNMC), DGA, DGPlano, DGPescas, DGAgriculture, DGFlorestas, DGUrbanismo, DGInfrastruturas, DGTransports, INE, INMG, PNO_ST e PNO_RAP | DUE Gabão, Albert Losseau | DGA, Eng. Lourenço Monteiro de Jesus
|  | Diagnosis of policy instruments and technical challenges in planning and implementation, and capacity building plan adapted to identified weaknesses elaborated | Ongoing | Agosto 2018 | Multi-sectoral | Adaptation | Consorcio QUAREIN/NIRAS, responsavel pela AT para a implementação do Projecto AMCC - Redução da Vulnerabilidade Climática em São Tomé e Principe | - Diagnóstico relativo aos déficits técnicos que poderão condicionar a viabilidade e a implementação do Projeto; - Diagnóstico dos instrumentos de política e das limitações técnicas ao nível da planificação e da implementação; - Proposta de plano de reforço de capacidades adaptado às fragilidades identificadas. |  | Comité Nacional para as Mudanças Climáticas (CNMC), DGA, DGPlano, DGPescas, DGAgriculture, DGFlorestas, DGUrbanismo, DGInfrastruturas, DGTransports, INE, INMG, PNO_ST e PNO_RAP | DUE Gabão, Albert Losseau | DGA, Eng. Lourenço Monteiro de Jesus
|  | Proposal for political, institutional and financial reform consistent with the challenges of the sectors, in particular in the coordination and management of the information elaborated, and the Adaptation objectives and priorities to be defined. | Ongoing | Fevereiro 2019 | Multi-sectoral | Adaptation | Consorcio QUAREIN/NIRAS, responsavel pela AT para a implementação do Projecto AMCC - Redução da Vulnerabilidade Climática em São Tomé e Principe |  |  | Comité Nacional para as Mudanças Climáticas (CNMC), DGA, DGPlano, DGPescas, DGAgriculture, DGFlorestas, DGUrbanismo, DGInfrastruturas, DGTransports, INE, INMG, PNO_ST e PNO_RAP | DUE Gabão, Albert Losseau | DGA, Eng. Lourenço Monteiro de Jesus
|  | Sector-specific agriculture policy and regulations drawn up and approved by the government |  |  | Agriculture | Adaptation
|  | Sector-specific policy and regulations for silviculture developed and approved by the government | Planned | 2023 | Forestry | Adaptation | FAO/GEF | FAO trabalhando em atualização do marco regulatório para florestas. Importante governo destacar esta necessidade que deve ser refletida no escopo da FAO |  | Direcção das Florestas/MADR |  | Lourenço Monteiro | Landscape Restoration for Ecosystem Functionality and Climate Change Mitigation in the Republic of São Tomé e Príncipe | Valor total do projeto FAO/GEF USD 4,666,515
|  | Policies and regulations for sustainable forestry management with the aim of increasing coastal climate resilience prepared and approved by the government | Planned | 2023 | Forestry | Adaptation | FAO/GEF | FAO trabalhando em atualização do marco regulatório para florestas. Importante governo destacar esta necessidade que deve ser refletida no escopo da FAO |  | Direcção das Florestas/MADR |  | Lourenço Monteiro |  | Valor total do projeto FAO/GEF USD 4,666,515
|  | Sector-specific policy and tourism regulations drawn up and approved by the government |  |  | Tourism | Adaptation
|  | Transports sectoral policy and regulations elaborated and approved by the government |  |  | Transport | Adaptation
|  | Sectoral policy and regulation approved by the government |  |  | Energy | Adaptation
|  | Water policy and sectoral regulations drawn up and approved by the government | Ongoing |  | Water | Adaptation | PNUD | Regulamentar a Lei Quadro dos Recursos Hidrícos: 1. Diploma Regulamentar que estabeleça a titularidade dos recursos hídricos; 2. Diploma Regulamentar sobre a inspeção, fiscalização e sanções; 3. Diploma Regulamentar que estabeleça sobre o regime de proteção das Waters superficiais e subterrâneas contra a poluição e deterioração; 4. Diploma regulamentar que estabeleça sobre o regime da qualidade da Water destinada ao consumo humano; 5. Diploma Regulamentar que estabeleça sobre o regime económico e financeiro dos recursos hídricos. 6. Orgânica da Entidade Gestora da àgua |  | MIRNA/DGRNE | Maite Mendizabal | Chicher Diogo | 94537-Projeto Energy | 40000
|  | Sectorial policy and regulation of fisheries developed and approved by the government |  |  | Fishery / Oceans | Adaptation
|  | Sector-specific solid waste management policy and regulations elaborated and approved by the government |  |  | Waste | Adaptation
| National strategy of resilient management for the maritime territory of STP elaborated | Completion of baseline studies to support strategy (to be defined between government and partner) |  |  | Fishery / Oceans | Adaptation
|  | Ocean management strategy to reflect the impacts of climate change on the oceans integrating actions adaptive to current and projected weather elaborated |  |  | Fishery / Oceans | Adaptation
|  | Strategy approved by the Government |  |  | Fishery / Oceans | Adaptation
| Regulation and instruments for land-use planning based on the risk of climatic and catastrophic impacts in coastal zones prepared and approved | Regulations and other specific instruments for risk-based spatial planning needs in coastal areas developed |  |  | Multi-sectoral | Adaptation
|  | Regulations and other specific instruments forland-use planning requirements approved |  |  | Multi-sectoral | Adaptation
|  | Selection of target communities identified by the government |  |  | Multi-sectoral | Adaptation
|  | Sustainable Community Plan Developed and approved for four communities |  |  | Multi-sectoral | Adaptation
| Resilient energy production and distribution strategy integrated into the Energy Plan | Intervention plan with priority activities to increase the resilience of the electricity sector of STP |  |  | Energy | Adaptation
|  | Integration of priority activities in the STP Energy Sector Development Plan |  |  | Energy | Adaptation
| Fisheries management practices adjusted to climate change scenarios | Number of fishing communities trained in Adaptation Good Practices and safety at sea | Planned | 2023 | Fishery / Oceans | Adaptation | Banco Mundial |  |  | DGA, Dir Pescas | Nicolas Desramaut | Arlindo Carvalho | WEST AFRICA COASTAL AREAS RESILIENCE INVESTMENT PROJECT (WACA) - PAMCZC II | 352000
|  | Number of trained fishermen | Planned | 2023 | Fishery / Oceans | Adaptation | Banco Mundial |  |  | DGA, Dir Pescas | Nicolas Desramaut | Arlindo Carvalho | WEST AFRICA COASTAL AREAS RESILIENCE INVESTMENT PROJECT (WACA) - PAMCZC II
|  | Capacity assessment of participants after completion of training |  |  | Fishery / Oceans | Adaptation
|  | Number of small Marinas built in vulnerable communities | Planned | 2023 | Fishery / Oceans | Adaptation | Banco Mundial | Planned 1 em Pantufo |  | DGA, Dir Pescas | Nicolas Desramaut | Arlindo Carvalho | WEST AFRICA COASTAL AREAS RESILIENCE INVESTMENT PROJECT (WACA) - PAMCZC II | 250000
|  | Number of structures for boats-protection built in vulnerable communities |  |  | Fishery / Oceans | Adaptation
| Transport infrastructure resilient to natural disasters and impacts of climate change built | Map of risks and intervention plan in the infrastructure of Transport | Planned | 2020 | Transport | Adaptation | Banco Mundial |  |  | INAE, Dir Transport | Nicolas Desramaut | Nelson Cardoso | Sao Tome e Principe Transport Sector Development and Coastal Protection Project | 250000
|  | Extension of roads (km) covered by risk reduction measures in the face of climate change | Planned | 2023 | Transport | Adaptation | Banco Mundial | Planned para 14 km da RN1 |  | INAE | Nicolas Desramaut | Nelson Cardoso | Sao Tome e Principe Transport Sector Development and Coastal Protection Project | 21000000
Strengthened coordination and information exchange processes to optimize and potentiate climate actions | Multisectoral coordination processes and National Climate Change Committee strengthened | Proposal for reorganization and operation of the National Committee on Climate Change (CNMC), and revision of Decree no. 13/2012, of May 29, prepared and presented to the government for approval | Ongoing | Setembro 2018 | Multi-sectoral | Cross-cutting | Consórcio QUAREIN/NIRAS, responsavel pela AT para a implementação do Projecto AMCC - Redução da Vulnerabilidade Climática em São Tomé e Principe |  |  | Comité Nacional para as Mudanças Climáticas (CNMC) e DGA | DUE Gabão, Albert Losseau | DGA, Eng. Lourenço Monteiro de Jesus | Projecto AMCC - Redução da Vulnerabilidade Climática em São Tomé e Principe
|  | Information dissemination and communication process of the CNMC formalized (Communication and website of the CNMC) | Ongoing | Agosto de 2018 | Multi-sectoral | Cross-cutting | Consorcio QUAREIN/NIRAS, responsavel pela AT para a implementação do Projecto AMCC - Redução da Vulnerabilidade Climática em São Tomé e Principe |  |  | Comité Nacional para as Mudanças Climáticas (CNMC) e DGA | DUE Gabão, Albert Losseau | DGA, Eng. Lourenço Monteiro de Jesus
|  | Technology and resources needed to map, monitor and evaluate projects related to MC in STP established: 1. Project management system 1.1 Project interconnection model with the accompanying indicators / NDC; 1.2 Real-time display panel of indicators performance in 1.1 over time; 2. Training of local information management services to support the control panel and maintenance of its structure and maintenance. | Ongoing | Novembro 2018 | Multi-sectoral | Cross-cutting | Consorcio QUAREIN/NIRAS, responsavel pela AT para a implementação |  |  | Comité Nacional para as Mudanças Climáticas (CNMC) e DGA | DUE Gabão, Albert Losseau | DGA, Eng. Lourenço Monteiro de Jesus
|  | Technological Support (computers, etc.) and infrastructure so that the Committee performs its functions, assured 1. Physical space for the headquarters of the NCCC provided by the MIRNA, in the DGA; 2. Equipment purchased (computers, printers, data-show, screen, furniture, etc.). 3. Graphic image of the NCCC and its Standards Guide | Concluded | - | Multi-sectoral | Cross-cutting | Orçamentos-Programa do Projecto AMCC - Redução da Vulnerabilidade Climática em São Tomé e Principe e Consorcio QUAREIN/NIRAS, responsavel pela AT para a implementação do Projecto AMCC - Redução da Vulnerabilidade Climática em São Tomé e Principe |  |  | Comité Nacional para as Mudanças Climáticas (CNMC) e DGA | DUE Gabão, Albert Losseau | DGA, Eng. Lourenço Monteiro de Jesus
|  | Additional support for the operationalization of the Committee (mobility, field operation, etc.) |  |  | Multi-sectoral | Cross-cutting
|  | Transparency platform that aggregates information on climate change and available databases in STP created 1. CNMC website; 2. Dashboard, real-time visualization, performance of projects and tracking indicators / NDC. | Ongoing | Novembro 2018 | Multi-sectoral | Cross-cutting | Consórcio QUAREIN/NIRAS, responsavel pela AT para a implementação do Projecto AMCC - Redução da Vulnerabilidade Climática em São Tomé e Principe |  |  | Comité Nacional para as Mudanças Climáticas (CNMC) e DGA | DUE Gabão, Albert Losseau | DGA, Eng. Lourenço Monteiro de Jesus | Projecto AMCC - Redução da Vulnerabilidade Climática em São Tomé e Principe
|  | Members of the Climate Change Committee, trained and competency assessment carried out and documented |  |  | Multi-sectoral | Cross-cutting
|  | Training to share georeferenced information and coordinate activities related to georeferenced data between institutions conducted and capacities assessed | Ongoing | Dezembro 2018 | Multi-sectoral | Cross-cutting | Banco Mundial |  |  | DGA, GNP, INM | Naraya Carrasco | Arlindo de Carvalho (DGA), Geisel de Menez (DNP)
| Coordination between international partners and the government strengthened | Consolidated process of coordination amongst international partners (annual meeting agenda, definition of group members, definition of communication processes and transparency and periodicity of meetings) |  |  | Multi-sectoral | Cross-cutting
|  | Execution of periodic meetings (every X months) of international partners to present projects In execution and Planneds and projects in planning |  |  | Multi-sectoral | Cross-cutting
|  | Results of exchanges between international partners documented to the STP government through the CNMC (annualy minimum) | Ongoing | anual (2018 e 2019) | Multi-sectoral | Cross-cutting | Consórcio QUAREIN/NIRAS, responsavel pela AT para a implementação do Projecto AMCC - Redução da Vulnerabilidade Climática em São Tomé e Principe |  |  | Comité Nacional para as Mudanças Climáticas (CNMC) e DGA | DUE Gabão, Albert Losseau | DGA, Eng. Lourenço Monteiro de Jesus | Projecto AMCC - Redução da Vulnerabilidade Climática em São Tomé e Principe
|  | Annual plan of activities of the National Committee on Climate Change and agenda of meetings and seminars | Ongoing | anual (2018 e 2019) | Multi-sectoral | Cross-cutting | Orçamentos-Programa do Projecto AMCC - Redução da Vulnerabilidade Climática em São Tomé e Principe e Consorcio QUAREIN/NIRAS, responsavel pela AT para a implementação do Projecto AMCC - Redução da Vulnerabilidade Climática em São Tomé e Principe |  |  | Comité Nacional para as Mudanças Climáticas (CNMC) e DGA | DUE Gabão, Albert Losseau | DGA, Eng. Lourenço Monteiro de Jesus
|  | Aid Information Management Systems (AIMS) implemented and regular publication of the Annual Cooperation Report |  |  | Multi-sectoral | Cross-cutting
|  | Periodic meetings (every x months) for sharing information between partners and government (UN-led co-ordination group and Climate Change Committee) |  |  | Multi-sectoral | Cross-cutting
| Consolidated and improved databases and information for better decision making and planning | Mapping, systematization and analysis of all information, studies and databases available in STP completed |  |  | Multi-sectoral | Cross-cutting
|  | Quality and accuracy of available information analyzed and studies to be updated proposed |  |  | Multi-sectoral | Cross-cutting
|  | Priority studies to support the climatic actions of STP (to be defined after consolidation of the two previous results) updated |  |  | Multi-sectoral | Cross-cutting
|  | Access to information regulated (define public and confidential information and access criteria) |  |  | Multi-sectoral | Cross-cutting
|  | Repository of online digital information (including available database, studies and projects) and regulation assigning responsibilities and competencies to update and disseminate information processes established | Ongoing | Dezembro 2018 | Multi-sectoral | Cross-cutting | Banco Mundial |  |  | DGA, GNP, INM | Naraya Carrasco | Arlindo de Carvalho (DGA), Geisel de Menez (DNP)
Strengthened mechanisms to measure, verify and report emissions of greenhouse gases | National inventory system implemented | National Inventory System (SNI) proposed |  |  | Multi-sectoral | Cross-cutting
|  | Approval of SNI proposal to the government |  |  | Multi-sectoral | Cross-cutting
|  | National Inventory System implemented |  |  | Multi-sectoral | Cross-cutting
Capacities to access and management of financial resources strengthened | National agencies accredited to the climate funds | National Agency accredited to GCF | Planned | 2019 | Multi-sectoral | Cross-cutting | GCF(Green Climate Fund) |  |  | DNP, INM,DGA | Stephanie CApedeVille, Eduardo Freitas | Fausto Neves | Fortalecimento da capacidade da Direção Nacional de Planeamento (Rediness Suport) | 300000
|  | Funds for which STP wants to be accredited selected and prioritized |  |  | Multi-sectoral | Cross-cutting
|  | National agencies selected and accredited with selected funds (if necessary / applicable) |  |  | Multi-sectoral | Cross-cutting
| Capabilities of national agencies to access and manage the resources available for climate change and enhanced development | Teams of STP agencies trained under the requirements and processes to access and manage funds from international funds and skills assessed |  |  | Multi-sectoral | Cross-cutting
|  | Processes of the national agencies adjusted / consolidated to meet the criteria of the selected funds |  |  | Multi-sectoral | Cross-cutting
|  | Independent audit on the use of funds published annually |  |  | Multi-sectoral | Cross-cutting
|  | Nr. of public servants and NGOs trained to prepare projects and access available international resources and skills assessed |  |  | Multi-sectoral | Cross-cutting
|  | Actors involved in the preparation and submission of projects and follow-up of projects in the English and French language trained and skills assessed |  |  | Multi-sectoral | Cross-cutting
| National capacities in the principles and practices of Forestry and Landscape Restoration (RFP), concepts and use of ecosystem services and RFP financial instruments reinforced | Capacity building program for RFP Platform Members, project partners and other stakeholders from the institutional, private and organized civil society sectors (in RFP principles, practices, ecosystem services, and related RFP and related financial instruments with payments for ecosystem services) | Planned | 2023 | Forestry | Cross-cutting | FAO/GEF |  |  | Direcção das Florestas/MADR |  | Lourenço Monteiro | LRI-Supporting Landscape and Livelihoods Resilience in Sao Tomé & Principe
|  | Identified path and capacity and consensus created for the opening of new lines of credit for actions related to RFP that can meet the needs of SMEs for the elaboration of a Code of Conduct to be adopted by ABSTP and other private financial entities | Planned | 2023 | Forestry | Cross-cutting | FAO/GEF |  |  | Direcção das Florestas/MADR |  | Lourenço Monteiro
|  | Evaluation study conducted on the National Fund for Forestry Development of STP (NFFD) and the Planned scheme of benefits and tax incentives and with recommendations for its improvement | Planned | 2023 | Forestry | Cross-cutting | FAO/GEF |  |  | Direcção das Florestas/MADR |  | Lourenço Monteiro
| TRI's RFP work is "expanded", triggering and supporting the development of public-private partnerships for nationally funded and implemented projects | Two medium-to-large-scale RFP projects (over USD 100k) developed through public-private partnerships between actors operating nationally by the end of the project. | Planned | 2023 | Forestry | Cross-cutting | FAO/GEF |  |  | Direcção das Florestas/MADR |  | Lourenço Monteiro
|  | Three small to mid-size (10-50kUSD) project funding RFP projects are initiated through public-private partnerships between actors that operate nationally by the end of the project. | Planned | 2023 | Forestry | Cross-cutting | FAO/GEF |  |  | Direcção das Florestas/MADR |  | Lourenço Monteiro
Strengthened communication and awareness-raising processes for climate change and the environment | National Policy on Environmental Education elaborated, implemented and monitored (forest, biodiversity, marine environment, water resources, waste, exploitation of natural resources, climate change) | National Plan of Environmental Education elaborated (contemplating the society as a whole - political decision makers at local and national level, students, teachers, private sector and civil society) |  |  | Multi-sectoral | Cross-cutting
|  | National Environmental Education Plan approved by the government |  |  | Multi-sectoral | Cross-cutting
|  | National Environmental Education Policy implemented and monitored |  |  | Multi-sectoral | Cross-cutting
|  | Environmental theme introduced in school textbooks since kindergarten, not only in the eighth year |  |  | Multi-sectoral | Cross-cutting
|  | Upper level course on environmental issues established |  |  | Multi-sectoral | Cross-cutting

## Drop down Menu
Setor | Status
Agriculture | Planned
Water | Ongoing
Construction | Concluded
Energy
Forestry | Foco
Industry | Adaptation
Multi-sectoral | Mitigation
Fishery / Oceans | Cross-cutting
Waste
Transport
Tourism